## Test Cases
| Test case | Jira | Kritinės klaidos | Nekritinės klaidos | Patikrinimu kiekis
1st sprint
| 005 | CPC-5 | 1 | 5 | 10
| 007 | CPC-7 | 2 | 2 | 6
| 010 | CPC-10 | 0 | 2 | 5
| 014 | CPC-14 | 1 | 5 | 10
| 015 | CPC-15 | 3 | 2 | 7
| 016 | CPC-16 | 0 | 2 | 5
| 017 | CPC-17 | 0 | 9 | 9
|  |  | 7 | 27 | 52 | Viso
2nd sprint
| 002 | CPC-2 | 2 | 5 | 20
| 003 | CPC-3 | 0 | 0 | 5
| 019 | CPC-19 | 0 | 0 | 3
| 021 | CPC-21 | 0 | 3 | 3
| 022 | CPC-22 | 2 | 0 | 6
| 024 | CPC-24 | 0 | 0 | 4
| LT Kalba | CPC-26 | 0 | 10 | 10
3rd sprint |  |  | 4 | 18 | 51 | Viso
| 0032 | CPC-28
| 000033 | CPC-29
| 000034 | CPC-30
| 000035 | CPC-31
| 000036 | CPC-32
| 000037 | CPC-33
| 000038 | CPC-34
| 000039 | CPC-35
| 000040 | CPC-1
|  | CPC-36 | backlog
|  | CPC-4 | backlog
|  | CPC-6 | backlog
|  | CPC-8 | backlog
|  | CPC-9 | backlog
|  | CPC-11 | backlog
|  | CPC-12 | backlog
|  | CPC-13 | backlog

## Lighthouse
|  | Entiries | 0 | 10 | 100 | 500 | 1000
| Units | [6 empty] | First Contentful Paint | Speed Index | Largest Contentful Paint | Time to Interactive | Total Blocking Time | Cumulative Layout Shift
PERFORMANCE | points |  | 68 | 67 | 59 | 52 | 48 | First Contentful Paint marks the time at which the first text or image is painted | Speed Index shows how quickly the contents of a page are visibly populated. | Largest Contentful Paint marks the time at which the largest text or image is painted. | Time to interactive is the amount of time it takes for the page to become fully interactive. | Sum of all time periods between FCP and Time to Interactive, when task length exceeded 50ms, expressed in milliseconds. | Sum of all time periods between FCP and Time to Interactive, when task length exceeded 50ms, expressed in milliseconds.
First Contentful Paint | s |  | 0.4 | 0.5 | 0.5 | 0.5 | 0.5
Speed Index | s |  | 0.8 | 0.9 | 1.1 | 1.5 | 2
Largest Contentful Paint | s |  | 2.3 | 2.3 | 2.2 | 2.3 | 2.2
Time to Interactive | s |  | 2.3 | 2.4 | 2.8 | 3.9 | 5.3
Total Blocking Time | ms |  | 440 | 470 | 780 | 1790 | 3550
Cumulative Layout Shift |  |  | 0 | 0.029 | 0.075 | 0.075 | 0.075
What to improve:
For page to load faster
Reduce unused JavaScript
Minify JavaScript
Avoid an excessive DOM size
Minimize main-thread work
Reduce JavaScript execution time